## Sheet1
Sprint | Task Id | Task Name | Status | Start date | End date
| 1 | Requirement Gathering | Completed | Oct 2 ,2021 | Nov 20,2021
| 2 | Feasibility Study | Completed
| 3 | Brainstorm | Completed
Sprint-1 | 4 | Proposal | Completed
| 5 | Wireframe for Splash Screen, Google verification (Allow, deny) and Welcome Screen | Completed
| 6 | Managing and Setting resources | Completed
| 7 | Wireframes | Completed
| 1 | Literature review | Completed | Nov 21,2021 | Dec 19,2021
Sprint-2 | 2 | Development of User Management System(Frontend ) | Completed
| 3 | Testing the pages | Completed
| 1 | Artefact designing report | Completed | Dec 20,2021 | Jan 24,2022
Sprint-3 | 2 | Development of User Management System (Backend ) | Completed
| 3 | Testing | Completed
Sprint-4 | 1 | Development of Jobs Management System (Frontend) | Completed | Jan 25,2022 | Feb 15,2022
| 2 | Testing | Completed
| 1 | Professionalism Report | Completed | Feb 16,2022 | Feb 27,2022
Sprint-5 | 2 | Development of Jobs Management System (Backend) | Completed
| 3 | Testing | Completed
| 1 | Development of Jobs Management System (Backend) | Completed | Feb 28,2022 | Mar 15,2022
Sprint-6 | 2 | Testing | Completed
| 1 | Working on the Final Report | Completed | March 16,2022 | March 25,2022
Sprint-7 | 2 | Finalization of Jobs Management System | Completed
| 3 | Testing | Completed
| 1 | Working on the Final Report | Completed | March 26,2022 | April 10,2022
Sprint-8 | 2 | Development of the recommendation system | Completed
| 3 | Testing | Completed
Sprint-9 | 1 | Development of the recommendation system | Completed | April 11,2022 | April 19,2022
| 2 | Testing | Completed
Sprint-10 | 1 | Development of Accessibility options | Completed | April 20,2022 | April 25,2022
| 2 | Testing | Completed
Sprint-11 | 1 | Finalization of report | Completed | April 30 ,2022 | April 30,2022
| 2 | Final System Testing | Completed